## Product Backlog
THE APPLICATION DEVELOPMENT PROJECT TOPIC
PRODUCT BACKLOG
Function Name | Feature | Complexity | Planned Code Iteration | In-charge Roll Number | In-charge Full Name | Actual Code Iteration
Home Page | Public | Complex | Iteration 1 | AnhLH | Lê Hoàng Anh | Iteration 1
Products List | Public | Complex | Iteration 1 | AnhLH, MinhVH | Lê Hoàng Anh, Vũ Nhật Minh | Iteration 1
Product Details | Public | Simple | Iteration 1 | AnhLH | Lê Hoàng Anh | Iteration 1
Cart Details | Public | Medium | Iteration 1 | AnhLH | Lê Hoàng Anh | Iteration 1
User Login | Common | Complex | Iteration 1 | HungND | Nguyễn Duy Hưng | Iteration 1
User Register | Common | Complex | Iteration 1 | HungND | Nguyễn Duy Hưng | Iteration 1
User Authorization | Common | Simple | Iteration 1 | HungND | Nguyễn Duy Hưng | Iteration 1
Admin Dashboard | Admin | Complex | Iteration 1 | TuanNA | Nguyễn Anh Tuấn | Iteration 1
Users List | Admin | Medium | Iteration 1 | TuanNA | Nguyễn Anh Tuấn | Iteration 1
Cart Completion (Place Order) | Public | Complex | Iteration 2 | AnhLH | Lê Hoàng Anh | Iteration 2
Reset Password | Common | Complex | Iteration 2 | HungND | Nguyễn Duy Hưng | Iteration 2
Change Password | Common | Medium | Iteration 2 | HungND | Nguyễn Duy Hưng | Iteration 2
User Profile | Common | Medium | Iteration 2 | HungND | Nguyễn Duy Hưng | Iteration 2
My Orders (xem lịch sử order) (tổng quát) | Customer | Medium | Iteration 2 | MinhVN | Vũ Nhật Minh | Iteration 2
Order Information (chi tiết) | Customer | Medium | Iteration 2 | TuanNA | Nguyễn Anh Tuấn | Iteration 2
Products List | Marketing | Medium | Iteration 2 | TuanNA | Nguyễn Anh Tuấn | Iteration 2
Customers List | Marketing | Medium | Iteration 2 | MinhVN | Vũ Nhật Minh | Iteration 2
Customer Details | Marketing | Simple | Iteration 2 | TuanNA | Nguyễn Anh Tuấn | Iteration 2
Sale Dashboard | Marketing | Medium | Iteration 2 | TuanNA | Nguyễn Anh Tuấn | Iteration 2
Orders List | Admin | Medium | Iteration 2 | MinhVN | Vũ Nhật Minh | Iteration 2
Order Details | Marketing | Medium | Iteration 2 | MinhVN | Vũ Nhật Minh | Iteration 2
Feedback | Public | Complex | Iteration 2 | DucDT | Đặng Trần Đức | Iteration 2
Feedbacks List | Marketing | Simple | Iteration 3 | DucDT | Đặng Trần Đức | Iteration 3
Feedback Details | Marketing | Simple | Iteration 3 | DucDT | Đặng Trần Đức | Iteration 3
Notification | Common | Simple | Iteration 3 | DucDT | Đặng Trần Đức | Iteration 3
Compare Product | Public | Medium | Iteration 3 | DucDT | Đặng Trần Đức | Iteration 3
Note:
BE: Back-end
FE: Front-end