## Wx
PROJECT REPORT
Group | 1 - SE1630-NET
Week | 05/09/2022-11/09/2022
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | SRS Document | In Progress
2 | Web Skeleton | Completed | Use Figma as the main tool to design screen mockup
3 | Design Database | In Progress
4 | Design Document | In Progress
5 | Work Division | Completed
5 | Product Backlog | Completed
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | SRS Document | HungND
2 | Web Skeleton
3 | Design Document | MinhVN
4 | Design Database | MinhVN
5 | Work Division
6 | Product Backlog | HungND
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
Pending
Pending
Pending
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Database Completion | 18/09/2022
2 | Design Completion | 18/09/2022
3 | SRS Document Completion | 18/09/2022
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
Note on C5: Author: Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on C23: Author: Pending: issue occurred, no solution yet In Progress: occurred and handling issue Completed: occurred and handled issue