## Product Backlog
THE APPLICATION DEVELOPMENT PROJECT TOPIC
PRODUCT BACKLOG
Function Name | Feature | Complexity | LOC | Planned Code Iteration | In-charge Roll Number | In-charge Full Name | Actual Code Iteration | SRS Status | Design Status | Coding Status | Testing Status | % Completed | Completed in Iteration
User Login | Common | Medium | 220 | Iteration 1 | HE130080 | Nguyễn Duy Hưng | Iteration 1 | Done | Doing | Done | Done | 90 | Iteration 1
User Register | Common | Medium | 220 | Iteration 1 | HE130080 | Nguyễn Duy Hưng | Iteration 1 | Done | Doing | Done | Done | 90 | Iteration 1
Home Page | Public | Medium | 220 | Iteration 1 | HE130782 | Lê Hoàng Anh | Iteration 1 | Done | Doing | Doing | Doing | 90 | Iteration 1
Products List (Customer) | Public | Complex | 300 | Iteration 1 | HE153050 | Vũ Nhật Minh | Iteration 1 | Done | Doing | Doing | Doing | 70 | Iteration 1
Cart Details | Public | Medium | 200 | Iteration 1 | HE130782 | Lê Hoàng Anh | Iteration 1 | Done | Doing | Doing | Doing | 60 | Iteration 1
Admin Dashboard | Admin | Complex | 300 | Iteration 1 | HE151491 | Nguyễn Anh Tuấn | Iteration 1 | Done | Doing | Doing | Doing | 70 | Iteration 1
Users List | Admin | Medium | 240 | Iteration 1 | HE151491 | Nguyễn Anh Tuấn | Iteration 1 | Done | Doing | Doing | Doing | 70 | Iteration 1
User Authorization | Common | Simple | 170 | Iteration 1 | HE130118 | Đặng Trần Đức | Iteration 1 | Done | Doing | Doing | Doing | 60 | Iteration 1
Product Details | Public | Medium | 200 | Iteration 2 | HE130782 | Lê Hoàng Anh | Iteration 2 | Done | Pending | Pending | Pending | 10 | Iteration 2 | ¦
Cart Completion (Place Order) | Public | Medium | 200 | Iteration 2 | HE130782 | Lê Hoàng Anh | Iteration 2 | Done | Pending | Pending | Pending | 10 | Iteration 2
Products List (Manager) | Marketing | Medium | 200 | Iteration 2 | HE153050 | Vũ Nhật Minh | Iteration 2 | Done | Pending | Pending | Pending | 10 | Iteration 2 | ¦
Customers List | Marketing | Medium | 200 | Iteration 2 | HE130080 | Nguyễn Duy Hưng | Iteration 2 | Done | Pending | Pending | Pending | 10 | Iteration 2
User Profile | Common | Medium | 200 | Iteration 2 | HE130080 | Nguyễn Duy Hưng | Iteration 2 | Done | Pending | Pending | Pending | 10 | Iteration 2 | ¦
My Orders (xem lịch sử order) (tổng quát) | Customer | Medium | 200 | Iteration 2 | HE153050 | Vũ Nhật Minh | Iteration 2 | Done | Pending | Pending | Pending | 10 | Iteration 2
Order Information (chi tiết) | Customer | Medium | 200 | Iteration 2 | HE153050 | Vũ Nhật Minh | Iteration 2 | Done | Pending | Pending | Pending | 10 | Iteration 2
Orders List | Marketing | Medium | 200 | Iteration 2 | HE130118 | Đặng Trần Đức | Iteration 2 | Done | Pending | Pending | Pending | 10 | Iteration 2
Order Details | Marketing | Medium | 200 | Iteration 2 | HE130118 | Đặng Trần Đức | Iteration 2 | Done | Pending | Pending | Pending | 10 | Iteration 2
Customer Details | Marketing | Simple | 100 | Iteration 2 | HE151491 | Nguyễn Anh Tuấn | Iteration 2 | Done | Pending | Pending | Pending | 10 | Iteration 2 | ¦
Sale Dashboard | Marketing | Medium | 200 | Iteration 2 | HE151491 | Nguyễn Anh Tuấn | Iteration 2 | Done | Pending | Pending | Pending | 10 | Iteration 2
Reset Password | Common | Complex | 300 | Iteration 3 | HE130080 | Nguyễn Duy Hưng | Iteration 3 | Done | Pending | Pending | Pending | 10 | Iteration 3
Change Password | Common | Medium | 200 | Iteration 3 | HE130080 | Nguyễn Duy Hưng | Iteration 3 | Done | Pending | Pending | Pending | 10 | Iteration 3
Feedback (Customer) | Public | Complex | 300 | Iteration 3 | HE151491 | Nguyễn Anh Tuấn | Iteration 3 | Done | Pending | Pending | Pending | 10 | Iteration 3
Feedbacks List | Marketing | Simple | 100 | Iteration 3 | HE130118 | Đặng Trần Đức | Iteration 3 | Done | Pending | Pending | Pending | 10 | Iteration 3
Feedback Details | Marketing | Simple | 100 | Iteration 3 | HE130118 | Đặng Trần Đức | Iteration 3 | Done | Pending | Pending | Pending | 10 | Iteration 3
Notification | Common | Simple | 100 | Iteration 3 | HE130782 | Lê Hoàng Anh | Iteration 3 | Done | Pending | Pending | Pending | 10 | Iteration 3
Compare Product | Public | Medium | 200 | Iteration 3 | HE153050 | Vũ Nhật Minh | Iteration 3 | Doing | Pending | Pending | Pending | 10 | Iteration 3
Note:
BE: Back-end
FE: Front-end